## Sheet1
|  | October | November | December | January | February | March | April
Project Brief
Background research
Write up
Time Management Planning
Final Gantt Chart
Research
Further background research
Literature review
Design
Planning diagrams (System overview, use-case, etc)
Progress report
Write up
Implementation
Account creation (Register)
Sign in
Add a partner
Create a form
Share a form
Sign out
Notifications
Testing
Robot Framework setup
Test implementation
Final report
Introduction, including: A clear statement of the problem and goals of the project
Background and Literature Review
Designs
Implementation
Testing and Software Validation
Results and Analysis
Evaluation
Project Management
Conclusions
Future Work
Bibliography
Appendices
Project viva
Viva